NEON CARTRIDGE LABS Company Launch & App Publishing Checklist Practical next steps after LLC, bank account, and domain setup

Purpose: Use this as the working checklist for getting Neon Cartridge Labs ready to operate, publish apps under the company name, and avoid the common blockers with Apple and Google developer accounts.

# 1. Must-have next steps

| Priority | Item | Why it matters |
| --- | --- | --- |
| 1 | Company email on domain | Needed for professional communication and Apple organization enrollment. |
| 2 | Simple public website | Google Play organization accounts require an organization website; it also builds trust. |
| 3 | D-U-N-S Number | Needed to verify the legal company for Apple and Google organization enrollment. |
| 4 | Support + privacy pages | Needed for app store listings and user trust. |
| 5 | Apple Developer Program organization account | Required to publish iOS apps under the company/legal entity name. |
| 6 | Google Play Console organization account | Required to publish Android apps under the company/developer name. |
| 7 | Operating Agreement | Defines ownership, responsibilities, decision-making, profit splits, and IP ownership. |
| 8 | Shared operational tools | Password manager, GitHub organization, Figma workspace, bookkeeping, and shared files. |

# 2. Company identity basics

Create a basic company identity layer before opening developer accounts. This makes the LLC look real and keeps the information consistent across Apple, Google, banking, tax, and app store profiles.

Domain email: hello@neoncartridgelabs.com

Support email: support@neoncartridgelabs.com

Privacy/legal email: privacy@neoncartridgelabs.com

Individual work emails: josue@neoncartridgelabs.com and javier@neoncartridgelabs.com

Business phone number that can receive verification calls/texts

Consistent legal name and address across LLC records, D-U-N-S, Apple, Google, bank, and payment profiles

# 3. Website pages to create

The website can be simple at first. It does not need to be a full agency site, but it should clearly identify the company and provide support/legal links for apps.

| Page | Purpose |
| --- | --- |
| Home | Short description of Neon Cartridge Labs and what the company builds. |
| Products / Apps | List current and upcoming apps. |
| Support | How users can get help. |
| Privacy Policy | Required or strongly expected for apps that collect any data. |
| Terms of Use | Recommended for apps, subscriptions, accounts, and paid features. |
| Delete Account / Data Request | Important if any app has login/accounts or stored user data. |
| Contact | Business contact details and email. |

# 4. D-U-N-S Number

The D-U-N-S Number should be treated as a publishing blocker. Request it or verify that the LLC already has one, and make sure the company name and address match the LLC documents.

Apple uses the D-U-N-S Number to verify organization identity and legal entity status during Apple Developer Program enrollment.

Google Play Console organization accounts list D-U-N-S, organization name, address, phone number, website, and contact details among the required information.

Use the same legal company name everywhere: Neon Cartridge Labs, LLC if that is the registered legal name.

# 5. Developer accounts

| Platform | Account type | Key notes |
| --- | --- | --- |
| Apple Developer Program | Organization | Apps are listed under the organization legal entity name. Requires D-U-N-S. Apple lists membership at 99 USD per year. |
| Google Play Console | Organization | Requires organization details such as D-U-N-S, organization website, phone number, and contact information. Google lists a one-time 25 USD registration fee. |

# 6. Internal roles for external use

Recommended simple titles for business cards, email signatures, and store/team identity:

| Person | Suggested title |
| --- | --- |
| Josue Aguilar | Co-Founder / Creative Director |
| Javier Hernandez | Co-Founder / Director of Operations |

# 7. Operational setup

Operating Agreement: ownership percentages, decision-making, roles, profit splits, buyout/exit terms, and IP ownership.

Bookkeeping: QuickBooks, Wave, Xero, or a CPA-managed spreadsheet from day one.

Password manager: 1Password or Bitwarden shared vault for developer accounts, domains, bank, tools, and API keys.

GitHub organization: repositories under Neon Cartridge Labs rather than personal accounts.

Figma workspace/project structure: company library, product files, brand assets, app store assets.

Shared file system: Google Drive or similar with folders for Legal, Finance, Brand, Products, App Store, and Marketing.

Stripe/payment account under the LLC if selling subscriptions, digital products, or direct purchases outside app stores.

# 8. Per-app publishing checklist

| Asset / Requirement | Status / Notes |
| --- | --- |
| App name |  |
| Bundle ID / package name |  |
| App icon |  |
| Screenshots |  |
| Short and long app descriptions |  |
| App category |  |
| Keywords / metadata |  |
| Privacy Policy URL |  |
| Support URL |  |
| Marketing URL |  |
| Age rating |  |
| Data safety / privacy answers |  |
| TestFlight or internal testing setup |  |
| App signing certificates / keys |  |
| Production build pipeline |  |

# 9. Recommended order of execution

Create company email with the domain.

Create the simple public website with Support and Privacy Policy pages.

Request or verify the D-U-N-S Number.

Finalize the Operating Agreement between Josue and Javier.

Create the Apple Developer Program organization account.

Create the Google Play Console organization account.

Create GitHub organization, Figma workspace, shared drive, and password manager.

Set up bookkeeping and basic finance tracking.

Prepare first app store assets and privacy/data answers.

Publish the first app under Neon Cartridge Labs.

# 10. Immediate blockers to resolve first

Focus first on: D-U-N-S, company domain email, public website, support/privacy pages, Apple Developer organization enrollment, and Google Play Console organization enrollment.

# Source notes

Official references used for account requirements and fees:

Apple Developer Program enrollment

Apple D-U-N-S help

Apple membership comparison / fee

Google Play Console required information

Google Play Console getting started / fee

Note: This is a practical startup checklist, not legal or tax advice. Use a CPA or attorney for operating agreement, tax classification, and compliance questions.